## Slide 1: E3VB Engineering Engagement Electrical Validation Board Project Proposal Presentation
January 2015
Team 12
Owners: Kris Gibbs, Brandon Towell, Luis Santiago, Travis Berger

## Slide 2: Proposal Outline
Improve Project Documentation
Develop a User Friendly Website
Get the Word Out About the Board
Add Content to Board Experiments
Improve the Board Documentation

## Slide 3: Improve Project Documentation
All documents must be formatted the same
Create both a student and instructor manual
Background theory
Make experiments as clear as possible

## Slide 4: Develop a User Friendly Website
Access to all experiments
Interaction Section

## Slide 5: Get the Word Out About the Board
Raise Board Exposure

## Slide 6: Add Content to Board Experiments
Add on to Current Experiments
Possibly Create New Experiments

## Slide 7: Improve the Board Documentation
Top Down Visual Aids
Clear locations

## Slide 8: Task Breakdown
Tasks
  Experiments
  Website Development
  Promotion

## Slide 9: Kris
Experiments
  Package Differences
  Simultaneous Switching Outputs
  Crosstalk I & II
Website Development
  Hosting
  Learning Language
  Writing Code

## Slide 10: Luis
Experiments
  Intersymbol Interference
  Driver Circuit
  Crosstalk I & II
Website Development
  Support Kris

## Slide 11: Travis
Experiments
  LCR Transmission Lines
  Corners & Vias
  Crosstalk I & II
Promotional
  Investigate Promotional Avenues
  Investigate Best Promotional Medium
  Create Promotional Project and Deliver Across Promotional Avenue

## Slide 12: Brandon
Experiments
  Mystery Traces
  Decoupling
  Crosstalk I & II
Promotional
  Investigate Promotional Avenues
  Investigate Best Promotional Medium
  Create Promotional Project and Deliver Across Promotional Avenue

## Slide 13: Timeline
Experiments Completion
  Preliminary Student Version: End of February
  Final Including Instructor Version: End of March
Website Completion
  Mid May – End of May
Promotion Completion
  Mid May