## Slide 1: E3VB Engineering Engagement Electrical Validation Board Project Proposal Presentation
January 2015
Team 12
Owners: Kris Gibbs, Brandon Towell, Luis Santiago, Travis Berger
Notes: Speaker – N/A
**Need to add PSU logo

## Slide 2: Background and Intro
Notes: Speaker - Unknown
Give current knowledge

## Slide 3: Proposal Outline
Improve Project Documentation
Develop a User Friendly Website
Get the Word Out About the Board
Add Content to Board Experiments
Improve the Board Documentation
Notes: Speaker - Travis

## Slide 4: Improve Project Documentation
All documents must be formatted the same
Create both student and instructor manuals
Background theory
Make experiments as clear as possible
Notes: Speaker - Travis
EE Students and above, CE students will not have background of Emag.

## Slide 5: Develop a User Friendly Website
Access to all experiments
Interaction section
Notes: Speaker - Kris
Interaction section deals with simulation only.
Access to experiments is strictly download and use offline, not to be used with control from the website or the computer.

## Slide 6: Get the Word Out About the Board
Raise Board Exposure
  Website
  Video
  Conferences
    Engineering
    Industrial
  IEEE
Notes: Speaker – Brandon
Research ECTC to find value in promoting there
IEEE Signal Integratea

## Slide 7: Add Content to Board Experiments
Add on to Current Experiments
Possibly Create New Experiments
Notes: Speaker – Travis
Add detail to what add on

## Slide 8: Improve the Board Documentation
Top Down Visual Aids
Clear locations
Notes: Speaker – Travis
Add detail to what add on

## Slide 9: Task Breakdown
Tasks
  Experiments
  Website Development
  Promotion
Notes: Speaker - Luis

## Slide 10: Kris
Experiments
  Package Differences
  Simultaneous Switching Outputs
  Crosstalk I & II
Website Development
  Hosting
  Learning Language
  Writing Code

## Slide 11: Luis
Experiments
  Intersymbol Interference
  Driver Circuit
  Crosstalk I & II
Website Development
  Support Kris

## Slide 12: Travis
Experiments
  LCR Transmission Lines
  Corners & Vias
  Crosstalk I & II
Promotional
  Investigate Promotional Avenues
  Investigate Best Promotional Medium
  Create Promotional Project and Deliver Across Promotional Avenue

## Slide 13: Brandon
Experiments
  Mystery Traces
  Decoupling
  Crosstalk I & II
Promotional
  Investigate Promotional Avenues
  Investigate Best Promotional Medium
  Create Promotional Project and Deliver Across Promotional Avenue

## Slide 14: Timeline
Experiments Completion
  Preliminary Student Version: End of February
  Final Including Instructor Version: End of March
Website Completion
  Mid May – End of May
Promotion Completion
  Mid May
Poster Presentation
  Mid May
Notes: Speaker – Kris
Draft of gantt chart